## Bright Coffee shop
| BRIGHT TV ANALYTICS | [5 empty] | Project start: | [7 empty] | 2026-04-01
| By Lungile Chirwa | [5 empty] | Display week: | [7 empty] | 1899-12-31
Project Phases
[7 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-03-30 to 2026-05-24
 | time axis 2026-03-30 to 2026-05-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
PLANNING
| Data flow chart | Lungile Chirwa | 100% | 2026-04-01 | 2026-04-03 | 3
| Proposal and feedback | Lungile Chirwa | 100% | 2026-04-03 | 2026-04-05 | 3
DATA PROCESSING
| Convert Excel to CSV file | Lungile Chirwa | 100% | 2026-04-04 | 2026-04-06 | 3
| Load data into databricks | Lungile Chirwa | 100% | 2026-04-04 | 2026-04-06 | 3
| SQL Transformation and cleaning | Lungile Chirwa | 100% | 2026-04-06 | 2026-04-07 | 2
| Create time buckets and calculate fied | Lungile Chirwa | 100% | 2026-04-06 | 2026-04-08 | 3
DATA ANALYSIS
| Export Processed data to excel | Lungile Chirwa | 100% | 2026-04-08 | 2026-04-10 | 3
| Create Pivot Tables | Lungile Chirwa | 100% | 2026-04-09 | 2026-04-11 | 3
| Build charts and dashboard | Lungile Chirwa | 100% | 2026-04-11 | 2026-04-12 | 2
| Behavioural Anaylsis | Lungile Chirwa | 100% | 2026-04-08 | 2026-04-13 | 6
| Insights | Lungile Chirwa | 100% | 2026-04-10 | 2026-04-14 | 5
PRESENTATION AND SUBMISSION
| Strategy and Recommended Design | Lungile Chirwa | 100% | 2026-04-10 | 2026-04-13 | 4
| Draft PowerPoint presentation | Lungile Chirwa | 100% | 2026-04-11 | 2026-04-13 | 3
| Stakeholder Review | Lungile Chirwa | 100% | 2026-04-13 | 2026-04-15 | 3